## Sheet1
Plan implement project proposal
Task |  |  | Total date | Design / and prepare |  |  |  |  | Code Mangement | Code customer
|  |  |  | 2016-06-01 |  |  |  |  | 2016-07-01 | jul-2016 (8)
|  |  |  | 24(end-13) | 25(end-20) | 26(end-27) | 28(end-3) |  | 28-29-30(end-25) | 31-32(end-4)
Management | Design Interface | Category page | 1.5 week
Write Post page
Product page
Account page
Bill page
| Database Design |  | 1 week
| Setup sping |  | 1 week
| Code |  | 3 week
Customer | Design Interface | Home page | 1.5 week
Login/Register page
View Read post
Show all category page
Cart page
| Code |  | 1.5 week
| Responsive |  | 3 date
Extend | Manager mobile
TimeShip