## Slide 1: Expected outcomes for 2nd year internship 2016

## Slide 2: Summary
Timeline
Project proposal
Meeting with Teachers 2 times for follow up
Full report
Poster
Presentation
Complete milestone timesheet each 2 weeks

## Slide 3: Timeline
06 June – 11 June: send project proposal to teachers
13 June – 17 June: 1st meeting with teachers to validate project proposal
11 July – 15 July: send draft report to teachers
18 July – 22 July: 2nd meeting with teachers to review draft report
05 August: deadline to send final package
15 August – 19 August: Presentation and Class council
22 August – 26 August: Revision Week
29 August – 01 September: Graduation Exam

## Slide 4: Project Proposal
Submit to teachers: 10 June 2016
Requirements:
  In Vietnamese and at least 3 pages
  Introduction part
    Describe reasons and objectives of project
  Detailed plan
    Describe technology and explain reasons why to choose this technology
    Describe tools to use and the benefits of the chosen tools
    Plan estimation
      Describe at least 3 milestones
    Images illustration
      At least 4 images
  Expected outcomes
    Describe what students want to achieve after the project
Note:
  In case Internal training full time, propose to company only 2 months training max and 1 month to implement project

## Slide 5: Meeting
1st meeting: 13 June – 17 June
  Review and validate project proposal
  Guide students and answer questions
  Discuss about next steps
  Receive feedbacks from students
2nd meeting: 18 July – 22 July
  Students must send draft report before
  Meet teachers to review report
  Discuss about next steps
  Receive feedbacks from students

## Slide 6: Full report
In Vietnamese
Deadline: 05 August
At least 25pages
  Company presentation : 2 pages
  Project Presentation/Proposal : 2 pages
  Software Requirements Specifications (SRS) : 10pages
    Example: http://www.cse.chalmers.se/~feldt/courses/reqeng/examples/srs_example_2010_group2.pdf
  Team work environment presentation and time management: 3 pages
  Day to day work : 3 pages
  Achievements : 2 pages
  Conclusion : 2 pages

## Slide 7: Poster
In English
Size A3
Content
  Subject
  Project Presentation and Objectives
  Development lifecycle/Flow
  Technologies
  Result
    Software Screenshot
    Conclusion

## Slide 8: Presentation
30 minutes
  20 minutes for presentation in English
  5 minutes for Q/A in Vietnamese
  5 minutes break
Presentation in English
  Company presentation : 2 minutes
  Project presentation : 2 minutes
  Working environment, team work and time management : 4 minutes
  Technical presentation : 10 minutes
    Flow and Technologies
    SRS
    Achievements
    Screenshots
  Conclusion : 2 minutes

## Slide 9: Milestone timesheet
Complete milestone timesheet each 2 weeks in Vietnamese and send
  To: IT Mentors
  CC: Ms. Thao Vi and Mr. Vinh
The content must be specific.

## Slide 10: BAD Milestone Timesheet
 | Week 1-2
What did you achieve | Study Java Apply HTML/CSS
What do you do currently | Study MySQL Study AngularJS
What do you plan to do | Study project

## Slide 11: GOOD Milestone Timesheet
 | Week 1-2 | Week 3-4
What did you achieve | Study and write Multithreading application in Java Apply advanced form in HTML5 in an web page | Hello World Program with AngularJS and review it with supervisor Apply Index Search in PHP Web pages
What do you do currently | Study Index Search in MySQL Write Hello World program with AngularJS | Write first draft of detailed project plan Discuss with supervisor for technology
What do you plan to do | Write detailed plan for project Ask supervisor for ideas and technology for project | Send first draft to teachers for validation Study the new technology that supervisor mentions.

## Slide 12: Mentors
WHO
  IT Teachers
ROLE
  Follow up student activities
    Check student milestone timesheet
    Ensure internship conditions match PN expectations
    Support the student facing difficulties
    Report difficulties to IT Coordinator
  Support student during the project
    Give advice about technique and work/time management
    Report difficulties to IT Coordinator
  Guide student for report writing
    Check draft report and ensure the student follow the right process
  Attend the presentation