**INTERNSHIP TRAINING PLAN**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Company name: TPP-FIT DANANG**  **Supervisor: Doan Tien Duy , Tran Van Nhu Tan**  **Department / division: Mobile Team**  **Phone: 0969 110 053**  **Email:** [**duydt.pnv@gmail.com**](mailto:duydt.pnv@gmail.com) | | | | **Trainee: Cao Ngoc Linh**  **Training duration:**480 hours | | |
|  | | | |  | | |
| **PRIMARY DESCRIPTION** | **EXPECTATION/OUTCOME** | **LEVEL** | **SUPERVISOR** | | **SHEDULE** |
| Basic Android Learning | Learning about Basic Android via a training flow chart  (Android Structure, Android Life Cycle, TextView, EditText, Button, ListView, Dialog, Webview…) | * Beginner | Doan Tien Duy | | 23 May 2016 – 04  June 2016 |
| Advance Android Learning | Learning about Advance Android via traning flow chart  (Custom all components in Android, Layout Params, XML Reading, Video,.. ) | * Intermediate | Doan Tien Duy | | 06 June 2016 – 18  June 2016 |
| Android – Web Service | Learning about Client & Server  Sending a data to server  Getting a data from server | * Intermediate | Doan Tien Duy – Tran Van Nhu Tan | | 20 June 2016 – 22  June 2016 |
| Android Game Learning | Searching about Game in Android  Writing algorithms for game | * Advanced | Doan Tien Duy | | 23 June 2016 – 27  June 2016 |
| Development Game Android | Development a game follow idea  Publishing this game to Google Play | * Advanced | Doan Tien Duy | | 28 June 2016 – 18  July 2016 |
| Company Project | Joining to a project of customer | * Advanced | Doan Tien Duy – Tran Van Nhu Tan | | 19 July 2016 – 12  August 2016 |